## Sheet1
Bug List
# | Reported Date | Reported By | Severity [P0-P5] | Status [open, in-progress, resolved, won't fix] | Assigned To | Short Desc. | Expected Results | Actual Results | Steps to reproduce
1 | 2024-02-16 | Daniel Lee | P2 | resolved | Daniel | When the character collides with a platform wall, it is expected to bounce back in the opposite direction. Instead, the character is currently passing through the wall | Upon colliding with the side of a platform, the character should rebound in the opposite direction of the wall | The character does not bounce back when colliding with the platform's wall but instead continues through the wall as if no collision occurred. | 1. Position the character adjacent to a platform wall. 2. Move the character towards the platform wall. 3. Observe the character's behavior upon collision with the wall.
2 | 2024-02-16 | Daniel Lee | P2 | resolved | Allan | The character is expected to come to a stop upon death with no animations playing. However, currently, the character continues to move horizontally after death, indicating that horizontal velocity is not being reset. | When the character dies (for example, by being hit by a falling boulder), all movement and animations should cease. | After the character is hit and the death event is triggered, the character continues to slide horizontally. | 1. Allow the character to be hit by the boulder to trigger the death sequence. 2. Observe the character's behavior following the death event.