## Sheet1
Bug List
# | Reported Date | Reported By | Severity [P0-P5] | Status [open, in-progress, resolved, won't fix] | Assigned To | Short Desc. | Expected Results | Actual Results | Steps to reproduce
1 | 2024-02-16 | Daniel Lee | P2 | resolved | Daniel | When the character collides with a platform wall, it is expected to bounce back in the opposite direction. Instead, the character is currently passing through the wall | Upon colliding with the side of a platform, the character should rebound in the opposite direction of the wall | The character does not bounce back when colliding with the platform's wall but instead continues through the wall as if no collision occurred. | 1. Position the character adjacent to a platform wall. 2. Move the character towards the platform wall. 3. Observe the character's behavior upon collision with the wall.
2 | 2024-02-16 | Daniel Lee | P2 | resolved | Allan | The character is expected to come to a stop upon death with no animations playing. However, currently, the character continues to move horizontally after death, indicating that horizontal velocity is not being reset. | When the character dies (for example, by being hit by a falling boulder), all movement and animations should cease. | After the character is hit and the death event is triggered, the character continues to slide horizontally. | 1. Allow the character to be hit by the boulder to trigger the death sequence. 2. Observe the character's behavior following the death event.
3 | 2024-03-24 | Brayden Shinkawa | P3 | resolved | Brayden | The character is expected to animate when moving immediately on input, however the movement inputs take an extra second to be noticed. The character will move but not animate for a second after input | When the character moves, the character should immediately start its running animation | The character takes an extra second after movement input to start its running animation. Releasing another key will also stop running animations | 1. Move the character 2. Observe the character not animate its movement in the first second of movement
4 | 2024-03-24 | Brayden Shinkawa | P2 | resolved | Aaron | When the character dies and the player continues drawing, the program should reset the scene. Instead, the game crashes | When the character dies and the game resets while the player's drawing, the game shouldn't crash | When the character dies and the game resets while the player's drawing, the game crashes | 1. Make the character die 2. While the character is dying, draw on screen 3. Keep drawing, game will crash
5 | 2024-03-24 | Joshua Chew | P3 | resolved | Joshua | When the character jumps or moves, the movement and jumping should be consistent across multiple machines. However, this is not the case | When comparing two machines running the game, both players should have similar jump heights and movement speeds | When comparing two machines running the game, players have differing jump heights and movement speeds | 1. Run the game on two different cpu setups 2. Compare jump height and speed of player 3. If different, problem is still present
6 | 2024-03-24 | Aaron Zhang | P4 | in progress | Joshua | When the character moves right and adds a short left movement, the player will continue to slide left even after the player stops pressing key inputs | When the character presses the A or D keys for moving left and right, they should move in their respective directions. If no keys are pressed, the player shouldn't move | Player continue moves without deaccelerating even when no input keys are pressed | 1. Make the character move right 2. Quickly press the left move button 3. Player should start sliding left without deaccelerating
7 | 2024-03-24 | Joshua Chew | P4 | in progress | Anyone | When the player respawns at a checkpoint flag, the checkpoint sound continues to play | When the player respawns at the checkpoint flag, no checkpoint sound should occur | When the player respawns at the checkpoint flag, the checkpoint sound repeats instead of staying silent | 1. Get player to hit a checkpoint (sound should play) 2. Get player to respawn at checkpoint by pressing L 3. Checkpoint sound will continue to repeat as long as the player stands on the checkpoint
8 | 2024-03-24 | Brayden Shinkawa | P5 | in progress | Anyone | When the player respawns and is falling down, they will be stuck in the running loop animation, even when not moving | When the player respawns, they should be in the neutral player texture frame | When the player respawns, they are stuck in the running loop animation, even when not moving | 1. Get player to respawn 2. player randomly respawns in run animation